## Issue Tracker
ID | Priority | Category | Issue | Why It Matters | Recommended Fix | Status
1 | Critical | Security | Product APIs not admin protected | Anyone can modify products/prices | Add admin role and protect write APIs | Open
2 | Critical | Checkout | Frontend cart not connected to backend | Orders are never really created | Use backend cart/order APIs | Open
3 | Critical | Pricing | Client controls prices | Users can manipulate prices | Calculate totals only on server | Open
4 | Critical | Data Security | Password hashes exported to S3 | PII/security risk | Exclude sensitive fields from exports | Open
5 | Critical | Authentication | Inactive users can still access system | Account deactivation ineffective | Validate account status on every request | Open
6 | Critical | Inventory | Stock race condition | Overselling products | Lock inventory during checkout | Open
7 | High | Auth | Forgot/Reset Password missing | Poor user experience | Implement password reset flow | Open
8 | High | Auth | Email verification missing | Fake/spam accounts possible | Add email verification | Open
9 | High | Auth | Change password UI missing | Users cannot manage credentials | Create security settings page | Open
10 | High | Orders | Order history missing | Users can't view purchases | Build order history page | Open
11 | High | Orders | Order tracking missing | No shipment visibility | Add tracking/status history | Open
12 | High | Payments | No real payment integration | Cannot process real payments | Integrate Razorpay/Stripe | Open
13 | High | Database | Inventory enum mismatch | Incorrect inventory auditing | Align with business requirements | Open
14 | High | Architecture | Startup migrations | Risky deployments | Use Alembic migrations | Open
15 | High | Security | JWT/localStorage issues | Session security risk | Use refresh tokens/httpOnly cookies | Open
16 | Medium | Database | Missing tables | Incomplete ecommerce flow | Add payments, reviews, wishlist, etc. | Open
17 | Medium | Performance | N+1 query issues | Slow performance at scale | Use eager loading | Open
18 | Medium | Testing | Broken test suite | No reliable validation | Fix test setup and fixtures | Open
19 | Medium | Search | Basic product search | Poor scalability | Add indexed search | Open
20 | Low | Code Quality | Dead code/unused files | Maintenance overhead | Clean up repository | Open

## Suggested Roadmap
Phase | Focus
Phase 1 | Security, Checkout, Pricing, Inventory
Phase 2 | Forgot Password, Email Verification, Order History
Phase 3 | Reviews, Wishlist, Coupons, Admin Dashboard